Examples of Completed VE Project Logframes, Budgets and Workplans

****Organisations can use these as a guide to assist in understanding how to complete the grants application form. Please do not use the exact examples below in your proposal

PROJECT OBJECTIVE, OUTCOMES AND OUTPUTS

First Example:

Second Example:

LOGFRAME EXAMPLES

First Example:

| Outcome 1: 5 guests have been fed at lunch-time (with at least one full plate of meet, porridge and dumplings) on 30 August 2008, for a cost not exceeding ZAR 20.- per plate |
| --- |
| Outputs | Activities | Indicators | Means of Verification |
| 1.) Meat has been prepared, cooked and served | Prepare, cook and serve meat | Guests eat all the meat served to them | Left-over bones, empty plate |
| 2.) Porridge has been prepared, cooked and served | Prepare, cook and serve porridge | Guests eat all the porridge served to them | Empty plate; eye-witness reports of compliments made to the host regarding excellent porridge |
| 3.) Dumplings have been prepared, cooked and served | Prepare, cook and serve dumplings | Guests eat all the dumplings served to them | Empty plate; eye-witness reports of compliments made to the host regarding excellent dumplings |

Second Example:

| Outcome 1: 60 housemother volunteers of X one-stop shelter in XYZ Province have received two 5-day workshops (one in June 2009 and one in November 2009) through recognized expert on how to monitor and interact with suicidal clients 24 hours/day, at a cost not exceeding ZAR 250000.- |
| --- |
| Outputs | Activities | Indicators | Means of Verification |
| Expert consultant recruited | Advertise consultancy Sunday Newspaper; interview candidates, and select preferred candidate | Training consultant has signed contract | Copy of contract document |
| Curriculum outline approved | Consultant develops curriculum and obtains approval of project coordinator | Training curriculum | Copy of training curriculum |
| First five-day training implemented | Select training date and venue; implement training | Participants have attended training at Conference Centre | Participation list; Copy of contract with Conference Centre |
| Second five-day training implemented | Select training date and venue; implement training | Participants have attended training at Conference Centre | Participation list; Copy of contract with Conference Centre |
| Training impacts assessed | Request feedback from trainees regarding first and second 5-day trainings. | Participants have expressed satisfaction and confirmed adequacy of training curriculum | Summary of evaluation results; copy of individual evaluation sheets |

EXAMPLES OF LOGFRAMES FOR OBLIGATORY M&E, CAPACITY BUILDING & GOVERNMENT INFORMATION EXCHANGE OUTCOMES

| Obligatory Outcome 1: Effective monitoring and evaluation of project activities, for a cost not exceeding ZAR XXX.- |
| --- |
| Outputs | Activities | Indicator | Means of Verification |
| M&E plan with clear targets for housemother training and coaching developed. | Develop project M&E plan | Assessment Instrument Tested | Assessment Report; Copy of Gantt Chart |
| Reporting mechanisms for housemother trainer, coaches and capacity development assistants established and operational | Communicate monthly reporting requirements to trainer / staff | No. Project staff trained in M&E. Monthly reports received in good quality | Training reports; samples of monthly reports |
| M&E mainstreamed into housemother work plans and work schedule. | Train housemothers how to report on client progress and service delivery | No. of housemother reports received in good quality | Copy of housemother reports |

| Obligatory Outcome 2: Enhanced staff capacity to manage and implement project activities, for a cost not exceeding ZAR XXX.- |
| --- |
| Outputs | Activities | Indicators | Means of Verification |
| Job ToRs presented to 8 Staff Members | Draft ToRs | ToR document available as part of project document | Copy of ToR |
| Signed Learning Contract | Discuss and draft learning goals | Staff member has defined learning goals for next 6 months | Copy of Learning Contract |
| 12 bi-monthly on-the-job performance M&E, and feedback provided | Observe staff member while carrying out responsibilities | Oral and written feedback provided, agreed and understood by staff member | Copy of feedback report |
| Staff performance evaluated | Meet with staff to assess learning achievements | Staff performance assessed | Copy of performance assessment containing signatures of both supervisor and staff |

| Obligatory Outcome 3: Effective exchange of information / communication on project achievements / results with government, for a cost not exceeding ZAR XXX.- |
| --- |
| Outputs | Activities | Indicators | Means of Verification |
| Project opening conference held with representatives of provincial government departments attending | Invite representatives, organize location, send out invitations | Conference held | Photos, list of participants attending conference |
| Midterm project progress report visit | Visit government counterparts to share mid-term project achievements | Meeting took place between CSO and government representatives | Photos, minutes of meeting |
| Project closing ceremony held | Invite community and government stakeholders | Closing ceremony held | Photo, press articles, invitation letters, agenda of ceremony |

###### EXAMPLE OF A VEP BUDGET

BUDGET (Please add rows and details as necessary. Please be as detailed and precise as possible. Please breakdown the total budget into proposed expenditure per quarter). This is a sample budget is for a 6 month training project.

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| ADMINISTRATIVE COSTS |  |  |  |  |  | FOR ADMIN COSTS ONLY |  |  |  |  |  |  |  |  |  |
| 1. Operational Staff (administrators, finance, logistics) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1. Project Coordinator | Person/ month | 1 | 6 | 28000 | 168000 | 50% | 84000 |  | 42000 | 42000 |  |  |  |  |  |
| 1.2. Training Coordinator | Person/ month | 1 | 5 | 11000 | 55000 | 100% | 55000 |  | 25000 | 30000 |  |  |  |  |  |
| 1.3. Office Assistant | Person/ month | 1 | 6 | 2000 | 12000 | 50% | 6000 |  | 3000 | 3000 |  |  |  |  |  |
| 1.4. Office Cleaner | Person/ month | 1 | 6 | 1600 | 9600 | 50% | 4800 |  | 2400 | 2400 |  |  |  |  |  |
| SUBTOTAL Operational Staff |  | 149800 |  | 72400 | 77400 |  |  |  |  |  |
| 2. Transport (car rent, kilometer claim) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. Kilometer claim | # of trips/number of km | 100 | 100 | 3 | 30000 | 100% | 30000 |  | 15000 | 15000 |  |  |  |  |  |
| 2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Transport |  | 30000 |  | 15000 | 15000 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| ADMINISTRATIVE COSTS |  |  |  |  |  | FOR ADMIN COSTS ONLY |  |  |  |  |  |  |  |  |  |
| 3. Public Transport (taxi, plane or bus tickets etc) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. Taxi fees to project sites | Taxi/ # Trips | 1 | 52 | 100 | 5200 | 100% | 5200 |  | 3000 | 2200 |  |  |  |  |  |
| 3.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Public Transport |  | 5200 |  | 3000 | 2200 |  |  |  |  |  |
| 4. Office expenditures (rent, electricity, water etc) | Rent per month, electricity etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. Office rent | # offices / month | 1 | 6 | 4500 | 27000 | 50% | 13500 |  | 6750 | 6750 |  |  |  |  |  |
| 4.2 Electricity | # offices / month | 1 | 6 | 1500 | 9000 | 50% | 4500 |  | 2250 | 2250 |  |  |  |  |  |
| 4.3 Water | # offices / month | 1 | 6 | 500 | 3000 | 50% | 1500 |  | 750 | 750 |  |  |  |  |  |
| 4.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Office Expenditures |  | 22650 |  | 9750 | 9750 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| ADMINISTRATIVE COSTS |  |  |  |  |  | FOR ADMIN COSTS ONLY |  |  |  |  |  |  |  |  |  |
| 5. Office furniture and technical equipment | piece |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1. Desk and Chair for Training Coordinator | piece | 1 | 1 | 3000 | 3000 | 100% | 3000 |  | 3000 |  |  |  |  |  |  |
| 5.2. Laptop for Training Coordinator | piece | 1 | 1 | 8000 | 8000 | 100% | 8000 |  | 8000 |  |  |  |  |  |  |
| 5.3. Book shelf for training coordinator | piece | 1 | 1 | 1000 | 1000 | 100% | 1000 |  | 1000 |  |  |  |  |  |  |
| SUBTOTAL Office furniture and technical equipment |  | 12000 |  | 12000 |  |  |  |  |  |  |
| 6. Communications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1. Cell Phone Units | recharge person/ month | 2 | 6 | 360 | 4320 | 100% | 4320 |  | 2160 | 2160 |  |  |  |  |  |
| 6.2. Land Line Fees | Fee / month | 1 | 6 | 500 | 3000 | 50% | 1500 |  | 750 | 750 |  |  |  |  |  |
| 6.3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Communications |  | 5820 |  | 2910 | 2910 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| ADMINISTRATIVE COSTS |  |  |  |  |  | FOR ADMIN COSTS ONLY |  |  |  |  |  |  |  |  |  |
| 7. Other Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Toner for Printer | Toner/ month | 1 | 6 | 1000 | 6000 | 50% | 3000 |  | 1500 | 1500 |  |  |  |  |  |
| 7.2 Photocopy | Number of copies/ month | 2500 | 6 | 1 | 15000 | 100% | 15000 |  | 7500 | 7500 |  |  |  |  |  |
| 7.3 Paper | Packet @ 500/ month | 1 | 6 | 180 | 1080 | 100% | 1080 |  | 1080 | 0 |  |  |  |  |  |
| 7.4 Misc. Stationary costs | Cost/ month | 1 | 6 | 500 | 3000 | 100% | 3000 |  | 1500 | 1500 |  |  |  |  |  |
| SUBTOTAL Other Costs |  | 22080 |  | 11580 | 10500 |  |  |  |  |  |
| SUBTOTAL ADMINISTRATIVE COSTS |  |  |  |  |  |  | 244000 |  | 126640 | 117760 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| OUTCOME 1: 60 Housemother Volunteers of 4 One-Stop-Shelters in Gauteng Province have received two five-day workshops through recognized expert on how to monitor and interact with suicidal clients 24 hours daily… |  |  |
| Output 1.1. Expert Training Consultant Recruited |  |  |  |
| a.) Advertise Vacancy in Sunday Newspaper | Announcement / # Sundays | 1 | 1 | 9600 | 9600 | 100% | 9600 |  | 9600 | 0 |  |  |  |  |  |
| Output 1.2. Curriculum Outline Approved |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) Consultant fee for curriculum and materials development | Consultant / day | 1 | 4 | 1500 | 6000 | 100% | 6000 |  | 6000 | 0 |  |  |  |  |  |
| b) Consultant travel (plane two-way ticket + taxi pick-up) to meet with project coordinator to share and discuss curriculum and pedagogical materials. | Ticket / person | 1 | 1 | 3700 | 3700 | 100% | 3700 |  | 3700 | 0 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| Output 1.3. First 5-day training implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) Consultant fee (including accommodation cost) | Consultant / day | 1 | 5 | 2000 | 10000 | 100% | 10000 |  | 10000 | 0 |  |  |  |  |  |
| c) Consultant travel (plane two-way ticket + taxi pick-up) | Ticket / person | 1 | 1 | 3000 | 3000 | 100% | 3000 |  | 3000 | 0 |  |  |  |  |  |
| d) Rental of two training venue | Venue / day | 2 | 5 | 950 | 9500 | 100% | 9500 |  | 9500 | 0 |  |  |  |  |  |
| e) Lunch / snacks | Person/ day | 60 | 5 | 350 | 105000 | 100% | 105000 |  | 10500 | 0 |  |  |  |  |  |
| f) Stationary | Person/ workshop | 60 | 1 | 100 | 6000 | 100% | 6000 |  | 6000 | 0 |  |  |  |  |  |
| g) Pedagogical materials | Person / # of copies | 60 | 50 | 1 | 3000 | 100% | 3000 |  | 3000 | 0 |  |  |  |  |  |
| h) Flipchart, etc. and Masking Tape | # Blocks @40 sheets /workshop | 1 | 3 | 130 | 390 | 100% | 390 |  | 390 | 0 |  |  |  |  |  |
| i) Whiteboard markers | # markers /workshop | 1 | 25 | 20 | 500 | 100% | 500 |  | 500 | 0 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| Output 1.4. Second 5-day training implemented |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) Consultant fee (including accommodation cost) | Consultant / day | 1 | 5 | 2000 | 10000 | 100% | 10000 |  | 10000 | 0 |  |  |  |  |  |
| c) Consultant travel (plane two-way ticket + taxi pick-up) | Ticket / person | 1 | 1 | 3000 | 3000 | 100% | 3000 |  | 3000 | 0 |  |  |  |  |  |
| d) Rental of two training venue | Venue / day | 2 | 5 | 950 | 9500 | 100% | 9500 |  | 9500 | 0 |  |  |  |  |  |
| e) Lunch / snacks | Person/ day | 60 | 5 | 350 | 105000 | 100% | 105000 |  | 10500 | 0 |  |  |  |  |  |
| f) Stationary | Person/ workshop | 60 | 1 | 100 | 6000 | 100% | 6000 |  | 6000 | 0 |  |  |  |  |  |
| g) Pedagogical materials | Person / # of copies | 60 | 50 | 1 | 3000 | 100% | 3000 |  | 3000 | 0 |  |  |  |  |  |
| h) Flipchart, etc. and Masking Tape | # Blocks @40 sheets /workshop | 1 | 3 | 130 | 390 | 100% | 390 |  | 390 | 0 |  |  |  |  |  |
| i) Whiteboard markers | # markers /workshop | 1 | 25 | 20 | 500 | 100% | 500 |  | 500 | 0 |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| Output 1.5. Training Impacts assessed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) Consultant fee for preparing impact / evaluation report (1st training) | Consultant / day | 1 | 1 | 1500 | 1500 | 100% | 1500 |  | 1500 | 0 |  |  |  |  |  |
| b) Consultant fee for preparing impact / evaluation report (2nd training) | Consultant / day | 1 | 1 | 1500 | 1500 | 100% | 1500 |  | 0 | 1500 |  |  |  |  |  |
| SUBTOTAL Outcome 1 |  | 297080 |  | 295580 | 1500 |  |  |  |  |  |
| OUTCOME 2: |  |  |  |  |  |  |  |  |  |
| Output 2.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 2.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Outcome 2 |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| OUTCOME 3: |  |  |  |  |  |  |  |  |  |
| Output 3.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Outcome 3 |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| OBLIGATORY OUTCOME 1: Effective monitoring and evaluation of project activities, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |  |
| Output 4.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| b) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Outcome 4 |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |

| EXPENDITURES | Unit Descrip-tion | No of Units (A) | No of Units (B) | Cost per Unit (in ZAR) | Total Cost (in ZAR) | % of Total Cost to be charged to project | TOTAL AMOUNT REQUESTED IN ZAR | EXPENDITURE 2009 | EXPENDITURE 2010 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-Jun | Q3 Jul-Sept | Q4 Oct-Dec |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| OBLIGATORY OUTCOME 2: Enhanced staff capacity to manage and implement project activities, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |  |
| Output 5.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Outcome 5 |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| OBLIGATORY OUTCOME 3: Effective exchange of information / communication on project achievements / results with government, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |  |
| Output 6.1. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 6.2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| a) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBTOTAL Outcome 6 |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| PROGRAMMATIC COSTS |  |  |  |  |  | 100% |  |  |  |  |  |  |  |  |  |
| SUBTOTAL PROGRAMMATIC COSTS |  |  |  |  |  | 100% | 297080 |  |  |  |  |  |  |  |  |
| TOTAL PROJECT COST (A+O) |  |  |  |  |  |  | 541480 |  |  |  |  |  |  |  |  |

EXAMPLE OF A VEP WORKPLAN

- WORK PLAN (Shade applicable areas and include target numbers for each quarter to measure achievements against performance indicators per quarter per line item. Please add more rows as necessary. Include all Outcomes.)

| PROPOSED PERFORMANCE TARGETS | 2009 | 2010 |
| --- | --- | --- |
| EXAMPLE | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4 | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4 |
| OUTCOME 1: 60 housemother volunteers of 4one-stop shelter in Gauteng Province have received two 5-day workshops (one in June 2008 and one in November 2008) through recognized expert on how to monitor and interact with suicidal clients 24 hours/day, at a cost not exceeding ZAR 250000.- |  | 60 | 60 |  |  |  |  |  |
| Output 1.1 Expert Training Consultant Recruited |  | X |  |  |  |  |  |  |
| Output 1.2 Curriculum Outline Approved |  | X |  |  |  |  |  |  |
| Output 1.3 First Five-Day Training Implemented |  | X |  |  |  |  |  |  |
| Output 1.3 Second Five-Day Training Implemented |  |  | X |  |  |  |  |  |
| Output 1.5. Training Impacts Evaluated |  | X | X |  |  |  |  |  |
| OUTCOME 2: |  |  |  |  |  |  |  |  |
| Output 2.1 |  |  |  |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |  |  |  |
| OUTCOME 3: |  |  |  |  |  |  |  |  |
| Output 3.1 |  |  |  |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |  |  |  |

o be continued, next page

Work plan, continued

| PROPOSED PERFORMANCE TARGETS | 2009 | 2010 |
| --- | --- | --- |
| EXAMPLE | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4 | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 4 |
| OBLIGATORY OUTCOME 1: Effective monitoring and evaluation of project activities, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |
| Output 1.1 Recruit expert consultant |  |  |  |  |  |  |  |  |
| Output 1.2 Agree on curriculum |  |  |  |  |  |  |  |  |
| OBLIGATORY OUTCOME 2: Enhanced staff capacity to manage and implement project activities, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |
| Output 2.1 |  |  |  |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |  |  |  |
| OBLIGATORY OUTCOME 3: Effective exchange of information / communication on project achievements / results with government, for a cost not exceeding ZAR XXX.- |  |  |  |  |  |  |  |  |
| Output 3.1 |  |  |  |  |  |  |  |  |

# Text boxes

Guests are hungry and thirsty

Problem Analysis

To provide adequate food and drink to guests

Overall, General Objective (Solution of Problem)

Outcome #1:

5 guests have been fed at lunch-time (with at least one full plate of meat, porridge and dumplings) on 30 August 2008, at a cost not exceeding ZAR  20.- per plate

Outcome #2:

5 guests have been served drinks at lunch-time (with at least one cup of tea, and/or one can of soft drink) on 30 August 2008 , for a total cost of ZAR 50.-

Specific Outcomes (concrete results necessary for producing solution)

1.)

Meat has been prepared, cooked and served

2.) Porridge has been prepared, cooked and served

3.) Dumplings have been  prepared, cooked and served

Outputs (action results that have been achieved)

1.) Soft drinks have been purchased, cooled and served

2.)

Tea has been purchased, heated up and served.

Outcomes (results necessary for producing solution)

Housemothers in one-stop shelters of XYZ Province do not have capacity to deal with suicidal clients

Problem

To better enable housemothers of one-stop shelters in XYZ Province to deal with suicidal clients

Objective (Solution of the Problem)

Outcome #1:

60 housemother volunteers of  X one-stop shelter  in XYZ Province have received two 5-day workshops  (one in June 2008 and one in November 2008) through Expert Dr. ABC on how to monitor  and interact with suicidal clients 24 hours/day, at a cost not exceeding ZAR 250000.-

Outcome #2:

5 guests have been served drinks at lunch-time (with at least one cup of tea, and/or one can of soft drink).

Outcome #2:

60 housemother volunteers of  X one-stop shelters in XYZ Province have been supervised and coached twice per week for 45 minutes (between July 2008 and October 2008) on how to interact with suicidal clients, at a cost not exceeding ZAR 100000.-

Outcome #3:

60 housemother volunteers of  X one-stop shelters in XYZ Province have visited one Model One-Stop Shelter in XXX Province to exchange experiences with professional housemothers prior to September 2008, for a cost not exceeding ZAR 40000.-

Training Consultant recruited

Consensus reached on Training Curriculum

Training Date and Venue selected

Logistical training support provided

Training impacts evaluated

Outputs (action results that have been achieved)